## WBS
Work Breakdown Structure | [5 empty] | Knowledge Space
© 2017 by Vertex42.com
| Project Start | 2020-03-21 |  |  |  |  | Work Breakdown Structure
Level | WBS | Task Description | Assigned To | Start | End | Notes
1 | 1 | Design and analysis |  |  |  |  | ◄ A Conditional Formatting rule formats Level 1 tasks
2 | 1.1 | Collecting requirement | Toan Bach
2 | 1.2 | Analyis requirement | Toan Bach
2 | 1.3 | Create user stories | Toan Bach
2 | 1.4 | Design solution architecture | Toan Bach
2 | 1.5 | Design functions | Toan Bach
2 | 1.6 | Design database structure | Toan Bach
1 | 2 | Technical preparation
2 | 2.1 | Setup development environment | Toan Bach
2 | 2.2 | Setup test environent | Toan Bach
2 | 2.3 | Create Git repository | Toan Bach
2 | 2.4 | Create source code structure | Toan Bach
1 | 3 | Implement Backend API
2 | 3.1 | Create entity classes | Toan Bach
2 | 3.2 | Configure entity classes using Fluent API | Toan Bach
2 | 3.3 | Configure Entity Framework Core | Toan Bach
2 | 3.4 | Configure ASP.NET Core Identity | Toan Bach
2 | 3.5 | Generate to Database | Toan Bach
2 | 3.6 | Configure Identity Server | Toan Bach
2 | 3.7 | Scaffold Identity UI | Toan Bach
2 | 3.8 | Install Swagger | Toan Bach
2 | 3.9 | Config swagger to accept authentication | Toan Bach
2 | 3.10 | Customize Identity Server for Authentication | Toan Bach
2 | 3.11 | Implement Role APIs | Toan Bach
2 | 3.12 | Add Fluent Validation | Toan Bach
2 | 3.13 | Add Unit tests | Toan Bach
2 | 3.14 | Implement User APIs | Toan Bach
2 | 3.15 | Implement function APIs | Toan Bach
2 | 3.16 | Implement permission APIs | Toan Bach
2 | 3.17 | Implement action Apis | Toan Bach
2 | 3.18 | Implement ticket APIs | Toan Bach
2 | 3.19 | Implement comment APIs | Toan Bach
2 | 3.20 | Implement Vote APIs | Toan Bach
2 | 3.21 | Implement Ticket Category APIs | Toan Bach
2 | 3.22 | Implement report Apis | Toan Bach
2 | 3.23 | Implement dashboard Apis | Toan Bach
2 | 3.24 | Apply permission to APIs | Toan Bach
1 | 4 | Implement Admin Angular
2 | 4.1 | Create Angular project | Toan Bach
2 | 4.2 | Create structure solution | Toan Bach
2 | 4.3 | Add template | Toan Bach
2 | 4.4 | Integrate login with Identity Server | Toan Bach
2 | 4.5 | Create common service | Toan Bach
2 | 4.6 | Create login page | Toan Bach
2 | 4.7 | Create menu | Toan Bach
2 | 4.8 | Config permission for menu | Toan Bach
2 | 4.9 | Create role page | Toan Bach
2 | 4.10 | Create user page | Toan Bach
2 | 4.11 | Create permission page | Toan Bach
2 | 4.12 | Create function page | Toan Bach
2 | 4.13 | Create ticket category page | Toan Bach
2 | 4.14 | Create ticket page | Toan Bach
2 | 4.15 | Create comment page | Toan Bach
2 | 4.16 | Create report page | Toan Bach
2 | 4.17 | Create dashboard page | Toan Bach
1 | 5 | Implement Web portal
2 | 5.1 | Create Web portal structure | Toan Bach
2 | 5.2 | Integrate with Identity Server | Toan Bach
2 | 5.3 | Add layout template | Toan Bach
2 | 5.4 | Integrate with Backend API common | Toan Bach
2 | 5.5 | Create home page | Toan Bach
2 | 5.6 | Create ticket list page | Toan Bach
2 | 5.7 | Create ticket detail page | Toan Bach
2 | 5.8 | Comment for ticket | Toan Bach
2 | 5.9 | Vote for ticket | Toan Bach
2 | 5.10 | Report for ticket | Toan Bach
2 | 5.11 | Profile page | Toan Bach
2 | 5.12 | Update profile page | Toan Bach
2 | 5.13 | Change password page | Toan Bach
2 | 5.14 | List ticket by user | Toan Bach
2 | 5.15 | Create new ticket | Toan Bach
2 | 5.16 | Notification SignalR | Toan Bach
1 | 6 | UAT | Toan Bach
1 | 7 | Deploy to production | Toan Bach
◄ Add new rows ABOVE this one.

## Help
HELP
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html |  | © 2017 Vertex42 LLC
About this Template
This template provides a very basic WBS table that you can use for defining a hierarchical work breakdown structure for a project plan or process.
Want more features and automation?
Try the Gantt Chart Template by Vertex42.com
Note: The formula for the WBS numbering was developed by Vertex42.com for the Gantt Chart Template Pro spreadsheet, and is copyrighted. See the terms of use.
Instructions
1) | Choose a Level from the drop-down list in column B. The WBS code is created automatically. When adding rows, you will need to copy the formula in the WBS code column into the newly added rows.
2) | Indent Task Descriptions using the Indent buttons in the Home tab.
3) | Add or hide columns as needed.
4) | A conditional formatting rule automatically highlights level 1 tasks. Go to Home > Conditional Formatting > Manage Rules to remove or edit this rule.
Terms of Use
See the following page for information about how you may use this spreadsheet.
https://www.vertex42.com/licensing/EULA_privateuse.html
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.